## Index
| <Project Name here> | Migration Runbook
Project Info
| Project Name | <project name> | Document Status | Draft
| Event | event | Version number | 5
Contact Info
| Primary Contact Name | Project Manager1 | Secondary Contact Name | Project Manager 2
| Pirmary Contact email |  | Secondary Contact email
| Primary Contact Phone # |  | Secondary Contact Phone #
| Bundle # | M1 | The information contained in this document is company confidential and is intended only for the use by the individuals directly engaged in the Data Center Relocation Project. If you are not, you are hereby notified that any dissemination, distribution or copying of this document or any disclosure of the contents of this document to others is strictly prohibited. If you have received this document in error, please notify the sender immediately and delete the original document and any copy of any e-mail and printout thereof.
Bundle Date
| Conference Bridge # | tbd
| Webex: | tbd
| Webex for Testers: | tbd
Web Portal URL
SUBJECT TO CHANGE - Refer to TransitionManager for latest
| Index (click to jump to tab): | Current Status | Final Team Review | Name | Date
1 | Staffing |  | DNS
2 | ChangeLog |  | Enterprise Firewalls
3 | Applications |  | PCN Firewalls
4 | Servers |  | Database
5 | Database |  | Virtual Machines
6 | Storage |  | Backup/Storage
7 | Other |  | Infrastructure
8 | Issues |  | Integration
9 | DNS-Network Configuration |  | Communications
10 |  |  | Estimated Start | Estimated Finish
11
12
13 | Premove Tasks
14 | Event Schedule |  | 0 | 0 | ~0 hrs
15 | Post-Move Tasks
16
17 | Lessons Learned | Ready

## ChangeLog
TransitionManager
Runbook ChangeLog
Manual changes made to this document by revision (excluding Pre-move completions)
Item # | Changes in Rev | App or Tab | Change Description | Change by | Requested by | Comments

## Staff
TransitionManager | [6 empty] | Logistics
Time periods
| Event Staff and Logistics | [5 empty] | 1 | 2 | 3 | 4
This table shows key staff for this event.
Source
General Personnel | [5 empty] | HQ
| Name | Move Role | Phone w | Phone c | Email | Target
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -
[7 empty] | - | - | - | -

## Applications
TransitionManager
| Applications |  | Mark exceptions in yellow
Listed below are the applications that will be impacted by this event. The impacted application may have some functionality impaired or be down completely.
Item | Application Name | Shutdown | Startup | Notes | SME | Manager | Coordinator | App Tester | Manager | Business Tester | Managers

## Servers
TransitionManager
Servers
| This is a list of any server or asset impacted on move day with From and To locations | [5 empty] | Servers :0 Blades: 0 VMs: 0
assetId | Application | Server | Comment | S/N | AssetTag | Manufacturer | Model | Type | Tasks on Shutdown | Tasks on Startup | Moving in M3 Weekend

## Database
TransitionManager
Databases
dbId | Name | Format | DBSize | Description | SupportType | Retire | MaintExp | Environment | MoveBundle | PlanStatus | Custom1 | Custom2 | Custom3 | Custom4 | Custom5 | Custom6 | Custom7 | Custom8

## Storage
TransitionManager
Logical Storage
StorageId | Name | Format | StorageSize | Description | SupportType | Retire | MaintExp | Environment | MoveBundle | PlanStatus | Custom1 | Custom2 | Custom3 | Custom4 | Custom5 | Custom6 | Custom7 | Custom8

## Other
assetId | Application | Server | ShortName | S/N | AssetTag | Manufacturer | Model | Type | IP | OS | SourceLoc | SourceRoom | SourceRack | SourcePos | Source Blade | Source Blade Position | TargetLoc | TargetRoom | TargetRack | TargetPos | Target Blade | Target Blade Position | Custom1 | Custom2 | Custom3 | Custom4 | Custom5 | Custom6 | Custom7 | Custom8 | MoveBundle | Truck | Cart | Shelf | RailType | Priority | PlanStatus | usize

## Issues
CommentId | Comment | commentType | AssetEntity | Resolution | Resolved By | Created By | Due Date | owner | category | Date Created | Date Resolved | Assigned To | Status | Predecessors | Duration | Estimated Start | Estimated Finish | Actual Time | Actual Finish | WorkFlow Step

## DNS-Network
TransitionManager |  |  |  | PLACEHOLDER
| DNS and Network Changes |  |  |  | Recent changes in Bold | [7 empty] | Old Primary DNS |  | Old Primary Wins
| This is a list of changes to server IPs and DNS |  |  |  | Dupes (some are ok) | missing data
Item # | Device Host Name(s) | Application* | OS Platform* | Mfg | Notes | Move Event | DNS Domain | Current IP Address | New IP Address | Subnet Mask | VLAN | Gateway Address | Primary DNS | Secondary DNS | Primary Wins | Secondary Wins

## Pre-move
TransitionManager |  |  | PLACEHOLDER
0
| Pre-Move Tasks |  | There are 0 tasks (0 overdue, 0 pending, and 7 needs a date) |  |  |  | 2016-09-28 13:57
0
Activities to be done prior to the migration event
Task # | Pred. | Application | Task Description | Responsible Resource | Status | Date Planned | Oustanding | Date Required | Comments | Duration | Estimated Start | Estimated Finish | Actual Time | Actual Finish | WorkFlow Step

## Schedule
TransitionManager
|  |  | Start Time: |  | 0
| Event Day Schedule | [45 empty] | Best prev
|  |  | Est Finish Time |  | 0 | [18 empty] | Citrix | Citrix | VM | VM | Sv | Sv | Sv | Sv |  |  |  |  | DB | DB | DB | DB | DB | DB | DB |  |  |  |  | time for |  | Best in
[18 empty] | TDS ASAP | TDS early | TDS | A | B | C | D | E | F | G | H | I | J | K | L | M | N | DB Team | DB 1 | DB 2 | DB 3 | DB 4 | DB 5 | DB 6 | DB 7 | P | Q | R | S | VM | VM | DB | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178
|  |  | Migration Activities | [11 empty] | Completion timeline | Max Pred | Pred count | [29 empty] | 999999 |  | 999999 | minute segments
Task # | Pre | Application | Task Description | Role | Responsible Resource | Intructions Link | Task Duration (min) | Duration | Estimated Start | Estimated Finish | Actual Time | Actual Finish | WorkFlow Step | Start | 0:00 |  |  | 0:00 | -0.375 | 0:00 | 2:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 |  |  |  | 0:15 | 0:30 | 0:45 | 1:00 | 1:15 | 1:30 | 1:45 | 2:00 | 2:15 | 2:30 | 2:45 | 3:00 | 3:15 | 3:30 | 3:45 | 4:00 | 4:15 | 4:30 | 4:45 | 5:00 | 5:15 | 5:30 | 5:45 | 6:00
Note on B7: Craig Macfarlane: If you use multiples, use 001,002 format or use spaces " 1, 2"

## Post-move
TransitionManager
Post-Move Tasks
Activities to be done after the migration event
Task # | Application | Task Description | Responsible Resource | Status | Date Planned | Date Complete | Comments | Predecessors | Duration | Estimated Start | Estimated Finish | Actual Time | Actual Finish | WorkFlow Step

## Learning
TransitionManager
Lessons Learned Template
Use this template to add issues learned from move to improve the next move.
Type | Category | Bundle Name | Date Open | Issue Identifier | Assignment Date | Resolution Due Date | Issue Severity | Issue Owner | Issue | Resolution | Future Preventive Measures | Future Prev Owner | Notes | Timeline Impact
Info Issue Lessons Learned | Migration; Facilities Logistics Network Storage Planning Communication | Pilot, M1, M2, M3 | MM/DD/YY | Name of Identifier | MM/DD/YY | MM/DD/YY | High Medium Low | Name of Owner | Text | Text | Text | Name |  | Time
Lessons Learned | Planning | Pilot | 2011-09-09 | Team | 2009-09-09 |  | High | Tim Schutt | Review meeting invitations missed important resources | This is an example issue in the template | Review meeting invitations will be validated prior to sending | Tim Schutt